## PROJECT LIST
Training Project
Tasks | Deadline | Start Date | Responsible | Progress to Date | Finish Date | Task Duration | Over/Under
Project Begins | 2022-02-01 | 2022-01-15 | Mary King | Completed | 2022-02-05 | 21 | 4
Interview Instructors | 2022-02-15 | 2022-01-30 | Shelly Rosen | Completed | 2022-02-02 | 3 | -13
Select Instructors | 2022-03-01 | 2022-02-01 | Gurpreet Singh | Started
Create Handouts | 2022-03-10
Set up Classrooms | 2022-03-15
Schedule Live Sessions | 2022-03-16
Schedule Virtual Training Sessions | 2022-03-16
Train Group A | 2022-04-01
Train Group B | 2022-04-05
Train Group C | 2022-04-15
Process Evaluations | 2022-04-20
Perform Post-Training Testing | 2022-04-25
Schedule Follow-Up Support Sessions (LIVE) | 2022-05-01
Schedule Follow-Up Virtual Support Sessions | 2022-05-01
Formulas:
Task Duration = DAYS([Finish Date],[Start Date])
Over/Under = DAYS([Finish Date],[Deadline])
Resources
Expenses
Students
Instructors

## RESOURCES
Training Project
Resource Name | Type | Role | Start Date | Hours / Units | Rate | Invoice Total | Notes
TechBooks, Inc. | Vendor | Course Materials | 2022-02-01 | 100 | 12.5 | 1250
Return to Project List

## EXPENSES
Training Project
Expense | Type | Start Date | Rate | Total Cost/Invoice | Approved for Payment? | Notes
Instructor Fees | Fees | 2022-02-20 | 85 | 25500 | Yes
Return to Project List

## STUDENTS
Training Project
Student Name | Department | Supervisor Approval? | Session Date | Completed? | Notes
Return to Project List

## INSTRUCTORS
Training Project
Instructor Name | Hourly Rate | Interviewed? | Approved? | Session Date/s | Contact Info | Notes
Return to Project List